## Slide 1: Degradation of bioplastics
By Pascal Visser, Rob Meulenkamp and Rienk Heins

## Slide 2: Goals of sprint 2
Finish data analysis
  Sort data
  Study variables
  Look at effects of special case samples
  Create final dataset
Start building a machine learning algorithm
  Start machine learning on smaller dataset

## Slide 3: Reordering of the data
Talk with Micha
Understanding the species cases
  Freeze taw
  Colouring
  Difference in samples
Reorganized data

## Slide 4: Freeze taw method
Method used in Micha's project to kill bacteria
Shows a disappearing cluster in samples following freeze taw

## Slide 5: Colouring of the data
Used in a few samples to detect plastics using fluorescence data
Could be used as a tool in later experiments

## Slide 6: PCA
Used to find variance in variables

## Slide 7: PCA
Used to find variance in variables

## Slide 8: Difference in samples

## Slide 9: Finalized dataset
Sample 1
No special cases
Incorrect files removed

## Slide 10: Positives
Found difference in bacteria and plastics with freeze taw
Better overview of data
Dataset that can be used for machine learning
Clearer idea for result

## Slide 11: Problems and bumps
Data processing took longer than planned
Machine learning not started yet
Data is hard to work with at times
Side goal of determining difference in bacteria seems unreachable

## Slide 12: Objectives for next sprint
Create machine learning algorithm
  Capable of classifying points as bacteria or plastics
  Able to show plastic degradation over time
  Usable to create a scoring system for plastic degradation

## Slide 13: Any questions?